## Sheet1
IMS - Estimation
Code Merging
S.No | Task | Sub Tasks | Estimation in Hrs | Status |  | Integration Testing
T A C
1 | Register Page | Low Level Design - Sequence Diagram | 0 |  |  | Compatibility testing
|  | HTML preparation | 1.5 |  |  | Deployment Documentation
|  | HTML Validations | 0
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1 |  |  |  | Open
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1 |  |  |  | Working
|  | Code Cleanup | 0.5
|  | Code Review | 0.5 |  |  |  | Completed
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7
2 | Login Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 2
|  | Web API - Service Implementation | 2.5
|  | Web API Integration | 1.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 13
3 | Current Drive Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 3
|  | HTML Validations | 1
|  | Web API - Service Implementation | 3
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 14
4 | Cancel Drive Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 3
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 12
5 | Scheduled Drive Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 11
6 | Upcoming Drive Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10
7 | Schedule a Drive Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 3
|  | HTML Validations | 1
|  | Web API - Service Implementation | 3
|  | Web API Integration | 1.5
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Integration Testing
|  | TOTAL | 15.5
8 | View profile Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10
9 | Dashboard Page | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 12.5
10 | All Scheduled Drives Page | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 12.5
11 | All Cancelled Drives Page | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 9.5
12 | Create Pool | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1.5
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 11.5
13 | Add Pool Members | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 4
|  | HTML Validations | 2
|  | Web API - Service Implementation | 3
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 16
14 | View Pool | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10.5
15 | View Pool Members | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 3
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 12.5
16 | Rename a Pool | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10
17 | Add Pool Members | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 0
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0
|  | Code Cleanup | 0
|  | Code Review | 0
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 6
18 | Rename a Pool Member | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 11
19 | Remove a Pool | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 9
20 | Create Invite | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API - Service Implementation | 3
|  | Web API Integration | 1.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Integration Testing
|  | TOTAL | 15
INTERVIEWER
21 | Register | Low Level Design - Sequence Diagram | 0
|  | HTML preparation | 0.5
|  | HTML Validations | 0
|  | Web API - Service Implementation | 2
|  | Web API Integration | 0.5
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 5.5
22 | Login | Low Level Design - Sequence Diagram | 0
|  | HTML preparation | 0
|  | HTML Validations | 0
|  | Web API - Service Implementation | 0
|  | Web API Integration | 0
|  | Swagger - API Documentation | 0
|  | Service Validations , Exception and Logging | 0
|  | Code Cleanup | 0
|  | Code Review | 0
|  | Unit Testing | 0
Integration Testing
|  | TOTAL | 0
23 | Todays Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 9.5
23 | Cancelled Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 10
24 | Scheduled Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 0.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 8
25 | Upcoming Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 0.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 8
26 | Profile | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 0.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 0.5
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 6
27 | Drive Invites | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10.5
28 | Drive Details | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 3
|  | HTML Validations | 2
|  | Web API - Service Implementation | 4
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Integration Testing
|  | TOTAL | 19
28 | Dashboard | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 7.5
29 | View All Drives | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 11
30 | Availability Given | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 9.5
31 | Utilized Slots | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7.5
32 | Not Utilized Slots | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7.5
33 | Invites Denied | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7.5
34 | Invites Ignored | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7.5
MANAGEMENT
35 | Register | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 2.5
|  | Web API - Service Implementation | 2.5
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 16
36 | Login | Low Level Design - Sequence Diagram | 0
|  | HTML preparation | 0
|  | HTML Validations | 0
|  | Web API - Service Implementation | 0
|  | Web API Integration | 0
|  | Swagger - API Documentation | 0
|  | Service Validations , Exception and Logging | 0
|  | Code Cleanup | 0
|  | Code Review | 0
|  | Unit Testing | 0
Integration Testing
|  | TOTAL | 0
37 | Todays Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 0.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 8
38 | Cancelled Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 10
39 | Scheduled Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 0.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 8
40 | Upcoming Interview | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 0.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 8
41 | Profile | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 0.5
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7.5
42 | Drive Invites | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 0.5
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 8
43 | Drive Details | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Integration Testing
|  | TOTAL | 10.5
44 | Dashboard | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 8.5
45 | View All Drives | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10
46 | Availability Given | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 9.5
47 | Utilized Slots | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7
48 | Not Utilized Slots | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7
49 | Invites Denied | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7
50 | Invites Ignored | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 7
51 | Pool Members Dashboard | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 13.5
52 | View All Pool Members Drives | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 11
53 | Pool Members Availability Given | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 11
54 | Pool Members Utilized Slots | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 9
55 | Pool Members Not Utilized Slots | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 9
56 | Pool Members Invites Denied | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 9
57 | Pool Members Invites Ignored | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Integration Testing
|  | TOTAL | 9
ADMIN
58 | Login | Low Level Design - Sequence Diagram | 0
|  | HTML preparation | 0
|  | HTML Validations | 0
|  | Web API - Service Implementation | 0
|  | Web API Integration | 0
|  | Swagger - API Documentation | 0
|  | Service Validations , Exception and Logging | 0
|  | Code Cleanup | 0
|  | Code Review | 0
|  | Unit Testing | 0
Integration Testing
|  | TOTAL | 0
59 | Dashboard | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 8.5
60 | View Accepted TAC Members | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10
61 | View Rejected TAC Members | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10
62 | Request From TAC | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 3
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Integration Testing
|  | TOTAL | 15.5
63 | Manage Location | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 10.5
64 | Manage Department | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 8
65 | Manage Project | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 8
66 | Manage Role | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Integration Testing
|  | TOTAL | 8
|  | ESTIMATTED HOURS : | 645
|  | BUFFER TIME : | 150 |  | ( 10 MEMBERS * 15 HOURS )
|  | TOTAL | 795
|  | ESTIMATTED DAYS: | 11.3 |  | ( 10 MEMBERS * 07HOURS PER DAY )