## Status Template - WEEK
Work Items | Completed | In Progress | Yet to start
Low Level Design | NIL | ADMIN User alone | Interviewer and TAC
Web API Implementation | Completed All Api methods except one functionality(Defaulters) | Fixing Small Bugs and Role Based Authourization | Defaulters Count & List in Management Dashboard
Angular Component Creation | Completed All Components creation | Updating small functionality changes(Form builder,CSS fixes) | NIL
Web API and Angular Integration | Admin User Intergreation. | Interviewer : Drive Invites & Dashboard TAC User : Dropdown Filters(Fixing bugs) | NIL
Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | Test cases for Controllers and Service layer for All Services | Test cases for DAL layer | Angular Component Testing
Refactoring and Deployment | NIL | NIL | Deployment and Refactoring( sonarqube )
Test Scenarios and Test Case Preparation | NIL | NIL | Test Scenarios and Test Case Preparation
Application Testing and Defects Tracking and Fixing | NIL | NIL | Application Testing and Defects Tracking and Fixing
Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | NIL | NIL | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots