## Actual Plan
WEEK 0 | 2022-03-21 | DAY 0 | INTRODUCTION AND ASSESSMENT | Completed
| 2022-03-22 | DAY 1 | REQUIREMENT PHASE | Completed
| 2022-03-23 | DAY 2 |  | Completed
| 2022-03-24 | DAY 3 | DESIGN PHASE | Completed
| 2022-03-25 | DAY 4 |  | Completed
WEEK 1 | 2022-03-28 | DAY 5 | DESIGN PHASE | Completed
| 2022-03-29 | DAY 6 |  | Completed
| 2022-03-30 | DAY 7 | CODING AND TESTING PHASE | Completed
| 2022-03-31 | DAY 8 |  | Completed
| 2022-04-01 | DAY 9 | PROJECT MANAGEMENT | Completed
| 2022-04-02 | DAY 10 | PROJECT KICKOFF | Completed
WEEK 2 | 2022-04-04 | DAY 11 | SPRINT 0 - Requirements Phase | Completed
| 2022-04-05 | DAY 12 |  | Completed
| 2022-04-06 | DAY 13 |  | Completed
| 2022-04-07 | DAY 14 |  | Completed
| 2022-04-08 | DAY 15 |  | Completed
| 2022-04-09 | DAY 16 | SPRINT 1 - Design Phase | Completed
WEEK 3 | 2022-04-11 | DAY 17 | SPRINT 1 - Design Phase | Completed
| 2022-04-12 | DAY 18 |  | Completed
| 2022-04-13 | DAY 19 |  | Completed
WEEK 4 | 2022-04-20 | DAY 20 | SPRINT 1 - Design Phase | Completed
| 2022-04-21 | DAY 21 |  | Completed
| 2022-04-22 | DAY 22 | SPRINT 2 - Coding Phase | Completed
| 2022-04-23 | DAY 23 |  | Completed
WEEK 5 | 2022-04-25 | DAY 24 | SPRINT 2 - Coding Phase | Completed
| 2022-04-26 | DAY 25 |  | Completed
| 2022-04-27 | DAY 26
| 2022-04-28 | DAY 27 | SPRINT 3 - Coding Phase
| 2022-04-29 | DAY 28
| 2022-04-30 | DAY 29
WEEK 6 | 2022-05-05 | DAY 30 | SPRINT 3 - Coding Phase
| 2022-05-06 | DAY 31
| 2022-05-07 | DAY 32 | SPRINT 4 - Testing Phase
WEEK 7 | 2022-05-09 | DAY 33 | SPRINT 4 - Testing Phase
| 2022-05-10 | DAY 34
| 2022-05-11 | DAY 35
| 2022-05-12 | DAY 36
| 2022-05-13 | DAY 37 | SPRINT 5 - Finalizing Phase
| 2022-05-14 | DAY 38
WEEK 8 | 2022-05-16 | DAY 39 | SPRINT 5 - Finalizing Phase
| 2022-05-17 | DAY 40
| 2022-05-18 | DAY 41
| 2022-05-19 | DAY 42 | PROJECT REVIEW
| 2022-05-20 | DAY 43
| 2022-05-21 | DAY 44

## Revised Plan
Day | Date | Phase | Work
Monday | 2022-05-09 | Coding Phase | Web API + Angular Component Creation Completion
Tuesday | 2022-05-10 | Coding Phase | Web API + Angular Component Creation Completion
Wednesday | 2022-05-11 | Coding Phase | Web API + Angular Component Creation Completion
Thursday | 2022-05-12 | Coding Phase | Web API + Angular Component Creation Completion
Friday | 2022-05-13 | Coding Phase | Web API + Angular Component Creation Completion
Saturday | 2022-05-14 | Coding Phase | Web API + Angular Component Creation Completion
Week 20 | 2022-05-14 | Status | Send the status as per the given table
Sunday | 2022-05-15 | LEAVE
Monday | 2022-05-16 | Coding Phase | Angular and Web API Integration
Tuesday | 2022-05-17 | Coding Phase | Angular and Web API Integration
Wednesday | 2022-05-18 | Coding Phase | Angular and Web API Integration
Thursday | 2022-05-19 | Coding Phase | Angular and Web API Integration
Friday | 2022-05-20 | Coding Phase | Angular and Web API Integration
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration
Week 21 | 2022-05-22 | Status | Send the status as per the given table
Monday | 2022-05-23 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing
Tuesday | 2022-05-24 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing
Wednesday | 2022-05-25 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing
Thursday | 2022-05-26 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing
Friday | 2022-05-27 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing
Saturday | 2022-05-28 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing
Week 22 | 2022-05-28 | Status | Send the status as per the given table
Sunday | 2022-05-29 | LEAVE
Monday | 2022-05-30 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing
Tuesday | 2022-05-31 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing
Wednesday | 2022-06-01 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing
Thursday | 2022-06-02 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages)
Friday | 2022-06-03 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages)
Saturday | 2022-06-04 | Coding Phase | Usability Testing - Lighthouse, https://validator.w3.org/ + Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages)
Week 23 | 2022-06-04 | Status | Send the status as per the given table
Sunday | 2022-06-05 | LEAVE
Monday | 2022-06-06 | Testing Phase | Test Scenarios and Test Case Preparation
Tuesday | 2022-06-07 | Testing Phase | Test Scenarios and Test Case Preparation
Wednesday | 2022-06-08 | Testing Phase | Test Scenarios and Test Case Preparation
Thursday | 2022-06-09 | Testing Phase | Application Testing and Defects Tracking and Fixing
Friday | 2022-06-10 | Testing Phase | Application Testing and Defects Tracking and Fixing
Saturday | 2022-06-11 | Testing Phase | Application Testing and Defects Tracking and Fixing
Week 24 | 2022-06-11 | Status | Send the status as per the given table
Sunday | 2022-06-12 | LEAVE
Monday | 2022-06-13 | Testing Phase | Application Testing and Defects Tracking and Fixing
Tuesday | 2022-06-14 | Testing Phase | Application Testing and Defects Tracking and Fixing
Wednesday | 2022-06-15 | Testing Phase | Application Testing and Defects Tracking and Fixing
Thursday | 2022-06-16 | Testing Phase | Application Testing and Defects Tracking and Fixing
Friday | 2022-06-17 | Testing Phase | Application Testing and Defects Tracking and Fixing
Saturday | 2022-06-18 | Testing Phase | Application Testing and Defects Tracking and Fixing
Week 25 | 2022-06-18 | Status | Send the status as per the given table
Sunday | 2022-06-19 | LEAVE
Monday | 2022-06-20 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots
Tuesday | 2022-06-21 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots
Wednesday | 2022-06-22 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots
Thursday | 2022-06-23 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots
Friday | 2022-06-24 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots
Saturday | 2022-06-25 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots
Week 26 | 2022-06-25 | Status | Send the status as per the given table
Sunday | 2022-06-26 | LEAVE
Monday | 2022-06-27 | Review | Reviewing the Application of all above mentioned activities
Tuesday | 2022-06-28 | Review | Reviewing the Application of all above mentioned activities
Wednesday | 2022-06-29 | Review | Reviewing the Application of all above mentioned activities
Thursday | 2022-06-30 | Review | Reviewing the Application of all above mentioned activities
Friday | 2022-07-01 | Review | Reviewing the Application of all above mentioned activities
Saturday | 2022-07-02 | LEAVE
Sunday | 2022-07-03 | LEAVE
Monday | 2022-07-04 | Demo | Demostration to Training and Delivery Team
Tuesday | 2022-07-05 | Demo | Demostration to Training and Delivery Team
Wednesday | 2022-07-06 | Demo | Demostration to Training and Delivery Team
Thursday | 2022-07-07 | Summary | Refershing all the topics and Feedbacks
Friday | 2022-07-08 | Summary | Refershing all the topics and Feedbacks
Saturday | 2022-07-09 | LEAVE
Sunday | 2022-07-10 | LEAVE

## References
.NET Test Explorer | https://codemag.com/Article/2009101/Interactive-Unit-Testing-with-.NET-Core-and-VS-Code?msclkid=39ec497bd10a11ec9fc571f847c244bb
https://levelup.gitconnected.com/unit-testing-best-practices-in-net-c-3117ea4010b9?sk=5b4cdac557b3e56d97365669a12aa198
Angular - Testing | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_test.htm
Linting | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_lint.htm
Doumentation | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_doc.htm
Pipelines | https://docs.aws.amazon.com/codepipeline/latest/userguide/tutorials-four-stage-pipeline.html#tutorials-four-stage-pipeline-add-stage
Security Testing | Automated Security Testing Using OWASP ZAP with Examples! (swtestacademy.com)
Performance Testing | https://www.simplilearn.com/tutorials/jmeter-tutorial/jmeter-api-testing
https://www.youtube.com/watch?v=HiRZq9_xDjg
Code Analysis | https://www.c-sharpcorner.com/article/step-by-step-sonarqube-setup-and-run-sonarqube-scanner/

## Status Template - WEEK <No>
Work Items | Completed | In Progress | Yet to start
Low Level Design | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API Implementation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Angular Component Creation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API and Angular Integration | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Refactoring and Deployment | * Source Code Repo | * Source Code Repo | * Source Code Repo
Test Scenarios and Test Case Preparation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Application Testing and Defects Tracking and Fixing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features

## Test Plan Template
<Project Name>Test Plan - <Cycle Number>
Scope of Test |  | Features Included | < Identify all software features and combinations of software features that will be tested.>
|  | Features Excluded | <Identify all features and significant combinations of features which will not be tested and the reasons.>
Test Deliverables |  |  | Identify the deliverable documents. You can list the following documents: - Test Plan - Test Cases - Test Incident Reports - Test Summary Reports>
Test Dependencies |  |  | <Identify significant constraints on testing, such as test-item availability, testing-resource availability, and deadlines.>
Test Environment |  | Hardware Environment | <Include the minimum hardware requirements that will be used to test the Application.>
Software Environment
Network and Communication
Test Items
S.No | Test Item |  | Source | [6 empty] | Version
Test Schedule
No. | Build | Features |  | Start Date | End Date | Actual Start Date | Actual End Date | Est Effort (in Hrs) | Actual Effort (in Hrs) | Completion % | Status
1
2
3
4
[5 empty] | Total |  | Total | 0 | 0 | #DIV/0!
Resources - Roles and Responsibilities
No. | Resource Name | Roles |  | Responsibilities
1
2
3
Depedencies
No. | Category | Description
1 | Software
2 | Resource
3 | Hardware
Assumptions
No. | Description
1
2
3

## Test Scenario Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Scenarios
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Reference Documents :
Assumptions /Constraints :
Date:
Scenario ID | Requirement ID | Module/Feature | Scenario Description
S_1 |  | Admin login to the application | Login page->Enter credentials->login
S_2 |  | Admin viewing the request received from the employee | Login->Employee request
S_3 |  | Admin accepting or rejecting employee request | Login->Employee request->Accept/reject
S_4 |  | Admin viewing list of department | Login->Manage Department
S_5 |  | Admin adding new Department | Login->Manage Department->Add Department->Enter department name->Add
S_6 |  | Admin removing existing department | Login->Manage Department->Remove icon->Remove
S_7 |  | Admin adding new location | Login->Manage Location->Add Location->Enter Location name->Add
S_8 |  | Admin viewing list of location | Login->Manage Location
S_9 |  | Admin removing existing location | Login->Manage Location->Remove icon->remove
S_10 |  | Admin adding new project | Login->Manage Project->Add Project->choose department->enter project name->Add
S_11 |  | Admin viewing list of project | Login->Manage Project
S_12 |  | Admin removing the existing project | Login->Manage Project->Remove icon->Remove
S_13 |  | Admin viewing list of Role | Login->Manage Role
S_14 |  | To add new management role | Login->Manage Role->Add Role->Enter Role name->
S_15 |  | To add new role
S_16 |  | Admin removing existing role | Login->Manage Role->Remove icon->Remove
S_17
S_18 |  | TAC login to the application | Login page->Enter credentials->login
S_19 |  | TAC viewing the home page | Login-> Home Page
S_20 |  | TAC viewing list of current drive | Login->Home->Current Drives
S_21 |  | TAC viewing list of current drive by department | Login->Home->Current Drives->Select Department
S_22 |  | TAC viewing list of current drive by department and its pool | Login->Home->Currrent Drives->Select Department and Pool
S_23 |  | TAC canceling the cuurent drives | Login -> Home-> Current Drives -> Cancel Drive -> Enter Reason -> Cancel Drive
S_24 |  | TAC viewing list of scheduled drives | Login->Home->Scheduled Drives
S_25 |  | TAC viewing list of scheduled drives by department | Login->Home->Scheduled Drives->Select Department
S_26 |  | TAC viewing list of scheduled drives by department and its pool | Login -> Home-> Scheduled Drives-> Select Department and Pool
S_27 |  | TAC canceling the schedule drives | Login -> Home-> Scheduled Drives -> Cancel Drive-> Enter Reason ->Submit
S_28 |  | TAC viewing list of upcoming drives | Login->Home->Upcoming Drives
S_29 |  | TAC viewing list of upcoming drive by department | Login->Home->Upcoming Drives->Select department
S_30 |  | TAC viewing the upcoming drive by department and its pool | Login -> Home-> Upcoming Drives-> Select Department, Select Pool
S_31 |  | TAC canceling upcoming drives | Login -> Home-> Upcoming Drives -> Cancel Drive-> Enter Reason ->Submit
S_32 |  | TAC viewing availabilities given by the employees for upcoming drives | Login -> Home-> Upcoming Drives -> View Availability
S_33 |  | TAC can schedule the interview for the emloyee who gave their availablity | Login->Home->Upcoming Drives->View Availability->Schedule
S_34 |  | TAC viewing his/her profile | Login->Profile
S_35 |  | TAC viewing their dashboard | Login-> Dashboard
S_36 |  | TAC viewing list of their scheduled drive | Login-> Dashboard -> Scheduled Drives
S_37 |  | TAC viewing list of their scheduled drive by department | Login->Dashboard->Scheduled Drives->Select Department
S_38 |  | TAC viewing list of their scheduled drive by department and pool | Login->Dashboard->Scheduled Drives->Select Department and then Select pool
S_39 |  | TAC viewing list of drives canceled by them | Login->Dashboard->Canceled Drives
S_40 |  | TAC viewing list of drives canceled by them by department | Login->Dashboard->Canceled Drives->Select Department
S_41 |  | TAC viewing list of drives canceled by them by department and pool | Login->Dashboard->Canceled Drives->Select Department and then select pool
S_42 |  | TAC creating a new pool | Login->Manage Pool->Create Pool->Choose department->Enter pool name->create
S_43 |  | TAC viewing list of pool | Login->Manage Pool
S_44 |  | TAC viewing list of pool by department | Login->Manage Pool->Choose Department
S_45 |  | TAC editing pool name | Login->Manage Pool->Edit icon->Enter pool name->Edit
S_46 |  | TAC removing the pool that has no active drives | Login->Manage Pool->Remove icon->Ok
S_47 |  | TAC adding pool members to a pool | Login->Manage pool->Manage pool members icon->click Right arrow to add
S_48 |  | TAC removing pool members from a pool | Login->Manage pool->Manage pool members icon->Left arrow to remove
S_49 |  | TAC adding pool members to a pool by role | Login->Manage pool->Manage pool members icon->select role->click Right arrow to add
S_50 |  | TAC adding pool members to a pool by name or ACE number | Login->Manage pool->Manage pool members icon->Search Name or ACE Number
S_51 |  | TAC adding pool members to a pool by role and its employee | Login->Manage pool->Manage pool members icon->Choose role->Search Name or ACE Number
S_52 |  | TAC creating a drive invite | Login->Create invite->Enter all the fields->create
S_53 |  | Interviewer login to the application | Login->Enter credentials->Login
S_54 |  | Interviewer viewing Home | Login->Home Page
S_55 |  | Interviewer viewing their Today's interviews | Login->Home->Today's Interviews
S_56 |  | Interviewer viewing their Today's interviews by pool | Login->Home->Today's Interviews->Select pool
S_57 |  | Interviewer viewing their scheduled interviews | Login->Home->Scheduled Interview
S_58 |  | Interviewer viewing their scheduled interviews by pool | Login->Home->Scheduled Interview->Select pool
S_59 |  | Interviewer viewing their scheduled interviews by date | Login->Home->Scheduled Interview->Select date
S_60 |  | Interviewer viewing their scheduled interviews by pool and date | Login->Home->Scheduled Interview->Select pool,select date
S_61 |  | Interviewer viewing their upcoming interview | Login->Home->Upcoming interview
S_62 |  | Interviewer viewing their upcoming interview by pool | Login->Home->Upcoming interview->Select pool
S_63 |  | Interviewer viewing their upcoming interview by date | Login->Home->Upcoming interview->Select date
S_64 |  | Interviewer viewing their upcoming interview by pool,date | Login->Home->upcoming interview->select pool,date
S_65 |  | Interviewer viewing their profile | Login->Profile
S_66
Other details
Author:
Reviewed by:
Approved by:
S_10 |  | To view list of project | Login->Manage Project

## Test Case Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Cases
Build/Release Version :
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Date:
Notes:
(Eg.) 1. This set of test cases should be run to check for the build fitness.
2. The tester should keep the back end (database) available and run an appropriate query to check the results / values displayed against the values shown in the front end.
Scenario ID | Test Case ID | Unit / Module or Location Description | Preconditions | Test Case Description | Test Steps | Test Data | Expected Result | Result (P/F/NT) | Defect ID | Comments
S_1 | TC_1 |  |  | Verify whether admin is able to login with valid ACE number and password | 1.In the login page ,admin Should enter valid ACE Number and Password 2.Then Admin Should click "Login" button | ACE Number:ACE0012 Password:Pass@12345 | Admin can able to login | P
S_1 | TC_2 |  |  | Verify whether admin is unable to login with valid ACE Number and Invalid Password | 1.In the login page ,admin Should enter valid ACE Number and invalid Password 2.Then Admin Should click "Login" button | ACE Number:ACE0012 Password:pass#1234 | 1.It should not allow Admin to login 2.It should display validation message for invalid Password 3.It Should Highlight "Wrong Password" | P
S_1 | TC_3 |  |  | Verify whether admin is unable to login with Invalid ACE Number and Valid Password | 1.In the login page,admin should enter Invalid ACE number and valid password 2.Then Admin Should click "Login" button | ACE Number:ACE0090 Password:Pass@12345 | 1.It should not allow Admin to login 2.It should display validation message for Invalid ACE Number 3.It Should Highlight " Password" | P
S_1 | TC_4 |  |  | Verify whether admin is unable to login with Invalid ACE Number and password | 1.In the login page,admin should enter invalid ACE Number and password 2.Then Admin Should click"Login" button | ACE Number:ACE0000 Password:admin | 1.It should not allow Admin to login 2.It should display validation message for Invalid ACE Number and Password 3.It Should Highlight " ACE Number"and Password | P
S_1 | TC_5 |  |  | Verify login page with blank fields and click login | 1. In the login page,click "Login" button without filling the fields | Not Applicable | 1.It should not allow admin to login 2.It should display validation message like"Fields are required" | P
S_2 | TC_6 |  |  | Verify admin is able to view the request received from the employee's after successful login | Not Application | Not Applicable | Able to view the request | P
S_3 | TC_7 |  |  | Verify whether admin is able to accept the request,so that they can able to login to their account | 1.Admin should click "Accept" button, once he/she verifies the employee. | Not Applicable | Able to accept the request | P
S_3 | TC_8 |  |  | Verify whether admin is able to reject the request,so that the employee unable to login | 1.Admin should click "Reject" buttton ,once he/she verifies the employee | Not Applicable | Able to reject the request | P
S_4 | TC_9 |  |  | Verify whether admin is able to view list of departments in Manage department | Not Applicable | Not Applicable | Able to view list of department | P
S_5 | TC_10 |  |  | Verify whether admin is able to add department with valid "department name" | 1.In the add department page,admin should enter the valid department name 2.Then click "Add" button | Department Name:LAMP | 1.Able to add the department successfully 2.It should display message "Department added successfully"in snack bar | P
S_5 | TC_11 |  |  | Verify whether admin is unable to add department ,if it already exists | 1.In the add department page,admin should enter the department name that already exist in database. 2.Then admin should click "Add" button | Department Name:LAMP | 1.Unable to add the department 2.It should display validation message as"Department name already exist" 3.It should highlight that field | P
S_5 | TC_12 |  |  | Verify whether admin is unable to add department ,if department name contains special characters and numbers | 1.In the add department page,admin should enter the department name that contains special characters and numbers 2.Then admin should click"Add" button | Department Name:Lamp12# | 1.Unable to add the department 2.It should display validation message 3.It should highlight that field | P
|  |  |  | Verify whether admin is able to add department,if department name contains dot(.) | 1.In the add department page,admin should enter the department which contains dot(.) 2.Then admin should click "Add" button | Department Name:.Net | 1.Able to add department 2.It should display message as "Department added successfully" | F
|  |  |  | Verify whether admin is unable to add department ,if name of the department is less than 3 characters | 1.In the add department page,admin should enter the department where name of the department is less than 3 caharacters | Department:aa | 1.Unable to add department 2.It should display validation message as"Department name is too short" | P
Verify whether admin unable to add department,when length of the department name is more than 15 characters
S_6 | TC_13 |  |  | Verify whether admin is able to remove department ,if he/she clicks "Remove" icon and confirms. | 1.In the manage department page,admin should click "Remove icon". 2.So that he/she prompts for confirmation, once confirms department get removed. | Not Applicable | 1.Able to remove the department. | P
S_6 | TC_14 |  |  | Verify whether admin is unable to remove department,if he/she click "Remove" icon but disprove | 1.In the manage department page,admin should click "Remove icon". 2.So that he/she prompts for confirmation, once he clicks"cancel" department won't get removed | Not Applicable | 1.Unable to remove department | P
S_7 | TC_15 |  |  | Verify whether admin is able to add Location with valid "Location name" | 1.In the add location page,admin should enter valid location name 2.Then click"Add" button | Location Name:Coimbatore | 1.Able to add location successfully 2.It should display message"Location added sucessfully" in snack bar | P
S_7 | TC_16 |  |  | Verify whether admin is unable to add Location ,when location already exist in database | 1.In the add location page,admin should enter loaction name which is already exist in database. 2.Then admin should click"Add" button | Location Name:Coimbatore | 1.Unable to add location 2.It should display message as "Location already exist" | P
S_7 | TC_17 |  |  | Verify whether admin is unable to add location ,when location name field is blank | 1.In the add location page,admin should click "Add" button without filling Location name | Not Applicable | 1.Unable to add location 2.It should display validation message | P
S_7 | TC_18 |  |  | Verify whether admin is unable to add Location ,when location name is invalid | 1.In the add location page,admin should enter location name,which consist of special characters and numbers. 2.Then admin should click"Add" button | Location Name:Chennai12# | 1.Unable to add location 2.It should display validation message | P
|  |  |  | Verify whether admin is unable to add Location,when location name is less than 3 characters | 1.In the add location page,admin should enter location name which should be less than 3 characters 2.Then admin should click"Add" button | Location Name:Ch | 1.Unable to add location 2.It should display validation message as "Location name is too short".
S_9 | TC_19 |  |  | Verify whether admin is able to remove location,when he/she clicks "Remove icon" and confirms | 1.In the manage location page,admin should click Remove icon . 2.Then it prompts for confirmation,once he/she confirms it get removed | Not Applicable | 1.Able to remove location successfully | P
S_9 | TC_20 |  |  | Verify whether admin is unable to remove location ,when he/she clicks "Remove icon" and disproves | 1.In the manage location page,admin should click Remove icon . 2.Then it prompts for confirmation,once he/she clicks "cancel" it won't get removed | Not Applicable | 1.Unable to remove location | P
S_8 | TC_21 |  |  | Verify whether admin is able to view list of location in manage location page. | Not Application | Not Applicable | 1.Able to view list of locations | P
S_10 | TC_22 |  |  | Verify whether admin is able to add project ,with valid project name under chosen department | 1.In the add project page,choose one department from the department dropdown 2.After that enter valid project name in the project name field and then click add button. | Department:.Net Project Name:IMS_DOTNET | 1.Able to add new project under the choosen department 2.It should display "Project Added Successfully" in snack bar | P
S-10 | TC_23 |  |  | Verify whether admin is unable to add project,with invalid project name under chosen department | 1.In the add project page,choose department from department dropdown 2.After that enter invalid project name like include some special characters and numbers and then click add button. | Department:.Net Project Name:IMS@#23 | 1.Unable to add new project under the choosen department. 2.It should display validation message | P
S_10 | TC_24 |  |  | Verify whether admin is unable to add project,with valid project name without choosing department | 1.In the add project page,if admin should not choose department but enters valid project name and then clicks add button | Department Name:- Project Name:IMS | 1.Unable to add new project 2.It should display message as"Choose a department" | P
S_10 | TC_25 |  |  | Verify whether admin is unable to add project,without project name but choosing department | 1.In the add project page,if admin should choose department from the department dropdown 2.But don't enter value in project name field and click add | Department Name:.Net Project Name:- | 1.Unable to add new project 2.It should display message as"Project Name is required" | P
S_10 | TC_26 |  |  | Verify whether admin is unable to add project,with blank fields | 1.In the add project page,without entering inputs,click add button | Department Name:- Project Name:- | 1.Unable to add new project . 2.It should display validation message 3.It should hightlight that field | P
S_11 | TC_27 |  |  | Verify whether admin is able to view list of project in Manage Project | Not Applicable | Not Applicable | 1.Able to view list of prjects | P
S_12 | TC_28 |  |  | Verify whether admin is able to remove the project,once he/she confirms | 1.In the Manage project page,click remove icon and then click "ok" | Not Applicable | 1.Able to remove project | P
S_12 | TC_29 |  |  | Verify whether admin is unable to remove the project,once he/she disproves | 1.In the Manage project page,click remove icon and then click "Cancel" | Not Applicable | 1.Unable to remove Project | P
S_13 | TC_30 |  |  | Verify whether admin is able to view list of role in Manage Role | Not Applicable | Not Applicable | 1.Able to view list of role in Manage role | P
S_16 | TC_31 |  |  | Verify whether admin is able to remove role,once he/she confirms | 1.In the Manage role ,click remove icon that prompts for confirmation then click "Ok" | Not Applicable | 1.Able to remove role successfully | P
S_16 | TC_32 |  |  | Verify whether admin is unable to remove role,once he/she disproves | 1.In the Manage Role,click remove icon that prompts for confirmation then click "Cancel" | Not Applicable | 1.Unable to remove role | P
|  |  |  | Verify whether TAC is able to create new pool with valid input | 1.In the Manage pool,click create pool and then choose the department and enter valid pool name 2.Then click "Add" button. | Deapartment: JAVA Pool Name:Fresher JAVA | 1.Able to create new pool 2.It should display message as"Pool Added successfully" in snack bar | P
|  |  |  | Verify whether TAC is unable to create new pool with invalid Pool Name(special characters) | 1.In the Add Pool page,choose the department from the department dropdown. 2.Then enter invalid Pool Name and then click "Add" button | Department Name:.Net Pool Name:Freshers####: | 1.Unable to create pool 2.It should display validation message | P
|  |  |  | Verify whether TAC is able to create new Pool that consist of numbers | 1.In the add pool page,choose the department from the deaprtment dropdown 2.Then enter pool name that consist of numbers | Department Name:.Net Pool Name:Freshers 2022 | 1.Able to create new pool 2.It should display message as"Pool Added successfully" in snack bar | F
|  |  |  | Verify whether TAC is unable to create new pool without choosing the department | 1.In tha add pool page,enter the valid pool name without choosing department from the department dropdown and then click "Add " button | Department Name:- Pool Name:Freshers | 1.Unable to create pool 2.It should display validation message as"choose a department " | P
|  |  |  | Verify whether TAC is unable to create a new pool with blank fields | 1.In the add pool page,click "Add" button without entering data | Not Applicable | 1.Unable to create new pool 2.It should display validation message as"choose a department" and "Pool name is required" | P
|  |  |  | Verify whether TAC is unable to create a new pool,when Pool Name lenght is greater than 25 | 1.In the add pool page,choose the deaprtment from the deaprtment dropdown 2.Then enter pool name which consist of more than 25 character | Department Name:.Net Pool Name:asdfghjkwertyuiozxcvbnmsdfghjsdfghjsdfghjsdfghjkdfghj | 1.Unable to create new pool 2.It should display validation message as"Pool Name must contain only alphabets and of lenght 3 to 25" | P
|  |  |  | Verify whether TAC is unable to create a new pool,when pool name lenght is less than 3 | 1.In the add pool page,choose the deaprtment from the deaprtment dropdown 2.Then enter pool name which consist of less than 3 character | Department Name:.Net Pool Name:cc | 1.Unable to create new pool 2.It should display validation message as "Pool name is too short" | P
|  |  |  | Verify whether TAC is able to view list of pool in Manage Pool | Not applicable | Not Applicable | 1.Able to view list of pool | P
|  |  |  | Verify whether TAC is able to view list of pool by department | 1.In the Manage pool,choose the department in department dropdown,to view list of pool for that department | Not Applicable | 1.Able to filter pool by department | P
Verify w
Other details
Author:
Reviewed by:
Approved by:
Test Results Reviewed by:

## Defect Log Template
Defect/Bug Report
Account/ Program Name
Project Name: | INTERVIEW MANAGEMENT SYSTEM
Defect Id(Required) | Defect Title | Related Module/Component | Detailed Defect Description | Defect Status | Defect Severity | Defect Priority | Defect Environment | Defect Injected Phase | Detected By | Detected in Phase | Detected in Version/Build | Defect Detected On Date | Fixed in version/Build No | Defect Category | Assigned to | Fixed on Date | Estimated Time To fix | Actual Time to Fix | Reopen Count
1 | Login | Login | Login Page is not responsive (Bg image and Title text alignment) | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
2 | Validation | Add Department | No spaces are accepted while adding a new department | Closed | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 |  |  |  | 2022-07-12
3 | Validation | Add Location | No spaces are accepted while adding a new location | Closed | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 |  |  |  | 2022-07-12
4 | Validation | Add Location | No multiple spaces are accepted, but no error message is thrown | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
5 | Dropdown filter | Interviewer- Today's Interviews | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
6 | Dropdown filter | Interviewer- Scheduled Interviews | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
7 | Dropdown filter | Interviewer- Upcoming Interviews | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
8 | Date Picker | Interviewer- Scheduled Interviews | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
9 | Date Picker | Interviewer- Upcoming Interviews | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
10 | Dropdown filter | Interviewer - Total no. of drives | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
11 | Dropdown filter | Interviewer - Availability Given | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
12 | Dropdown filter | Interviewer - Utilized Interviews | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
13 | Dropdown filter | Interviewer - Not Utilized Interviews | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
14 | Dropdown filter | Interviewer - Drives Ignored | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
15 | Dropdown filter | Interviewer - Drives Denied | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
16 | Date Picker | Interviewer - Total no. of drives | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
17 | Date Picker | Interviewer - Availability Given | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
18 | Date Picker | Interviewer - Utilized Interviews | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
19 | Date Picker | Interviewer - Not Utilized Interviews | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
20 | Date Picker | Interviewer - Drives Ignored | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
21 | Date Picker | Interviewer - Drives Denied | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12
22 | Date Picker | Interviewer - Accept Invite page | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [13 empty] | Root cause | Communication Gap
23 | Time picker | Interviewer - Accept Invite page | Time picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Defect Status |  | Defect Severity- | Defect Priority | Defect Environment |  |  | Lack of Domain Knowledge
24 | Reject page | Interviewer - Drive Invites page | Functionality Issue | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | New |  | Critical | High | Development |  |  | Competency
25 | Dropdown filter | TAC - Current Drive page | Department & pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Open |  | Major | Critical | Integration Testing |  |  | Lack of EndUser Input
26 | Dropdown filter | TAC - Scheduled Drive page | Department & pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Assigned |  | Minor | Medium | System Testing |  |  | Lack of Standards and Guidelines
27 | Dropdown filter | TAC - Upcoming Drive page | Department & pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Fixed |  | Trivial | Low | Pre-Production |  |  | Environment
28 | Date Picker | TAC - Scheduled Drive page | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Closed |  |  |  | UAT |  |  | Requirements not captured
29 | Date Picker | TAC - Upcoming Drive page | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Rejected |  | Defect Type |  | Production |  |  | Requirements captured incorrectly
30 | Font style | TAC - Cancelled Drive History page | "Cancellation Reason" font is different | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Deferred |  | Review |  |  |  |  | Incomplete screen design
31 | Routing | TAC - Add Pool | Sidebar is not active when "Add Pool" is clicked | Closed | Minor | Low | System Testing | coding | Development | Release |  | 2022-07-12 |  |  |  | 2022-07-12 | [5 empty] | Testing |  |  |  |  | Incorrect screen design
32 | Pool | TAC - Add Pool | Department name should be choosen first & Pool name should be given next | Closed | Major | High | System Testing | coding | Development | Release |  | 2022-07-12 | [14 empty] | Incomplete database design
33 | Drive History | TAC - Cancelled Drive History page | Department dropdown is not listing the departments | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-12 | [14 empty] | Incorrect database design
34 | Response | TAC - View Drive Response page | "No records found" message is displayed even after Response is displayed | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-12 | [14 empty] | Incomplete report layout
35 | Routing | TAC - Cancel Drive page | Sidebar is not active when "Cancel" button is clicked | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [14 empty] | Incorrect report layout
36 | Font style | TAC - Cancel Drive page | Cancel Reason is not bold and should be renamed as "Cancellation Reason" | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [14 empty] | Incomplete interface definition
37 | Spelling mistakes | TAC - MyPerformance page | Grammatical mistakes & punctuation mark in cards(Scheduled,Cancelled drives) | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [14 empty] | Incorrect interface definition
38 | Scheduled Drive | TAC - Scheduled Drive page | Reason is not required in the card for scheduled drive | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-12 | [7 empty] | Defect Injected Phase | Maintenance: | Development | Detected By | Defect Category | Missed Requirements |  | Incomplete security design
39 | Dropdown filter | TAC - Create Invite page | Department dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [8 empty] | Requirements | Requirements | QA |  | UI Issues |  | Incorrect security design
40 | Dropdown filter | TAC - Create Invite page | Pool dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [8 empty] | Analysis | Design | Internal Customer |  | Functional Issues |  | Incorrect functionality
41 | Dropdown filter | TAC - Create Invite page | Mode dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [8 empty] | Design | Coding | External Customer |  | Performance Issues |  | Incorrect / not optimized SQL
42 | Dropdown filter | TAC - Create Invite page | Location dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [8 empty] | coding | Release | Development |  | Non Functional |  | Incorrect logic in design
43 | Dropdown filter | TAC - Create Invite page | Slot Timing dropdown is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [8 empty] | Release |  |  |  | Security |  | Incomplete Unit Test Cases
44 | Date Picker | TAC - Create Invite page | From Date date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-12 | [12 empty] | Environment Issues |  | Incorrect Unit Test Cases
45 | Date Picker | TAC - Create Invite page | To Date date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-13 | [12 empty] | Upgrade Issue |  | Incomplete Integration Test Cases
46 | Date Picker | Interviewer - Accept Invite page | Size of the Availability Date picker is small | Closed | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-13 | [12 empty] | Database connectivity issues |  | Incorrect Integration Test Cases
47 | Responsiveness | Interviewer - Accept Invite page | Date picker is not responsive | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-13 | [12 empty] | Cosmetic issues(Its Comes for Spelling Mistakes and color changes in prompts, It is like minimal changes/) |  | Incomplete Functional Test Cases
48 | Misalignment | Interviewer - Accept Invite page | Time picker's hour & minute is misaligned | Open | Minor | Low | System Testing | coding | Development | Release |  | 2022-07-13 | [12 empty] | Database Error |  | Incorrect Functional Test Cases
49 | Sorting | Interviewer - Drive Invites page | Sort the invites based on recent invite | Open | Major | Medium | System Testing | coding | Development | Release |  | 2022-07-13 | [12 empty] | Data Error |  | Code missing
50 | Date Correction | Interviewer - Accept Invite page | Date Format of From & To Date should be changed | Closed | Major | Medium | System Testing | coding | Development | Release |  | 2022-07-13 | [12 empty] | Typo Error |  | Incorrect logic in code
51 | Filterdropdown | Create account | Project is not filtered according to the department | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13 | [14 empty] | Exception handling error
52 | Error message | Create account | "Wait for Administrator's verification" message is not proper | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13 | [14 empty] | Not a Defect
53 | Validation | TAC Create Invite | Repeated Character is accepted in Drive Name | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13 | [14 empty] | Incomplete Documentation
54 | Validation | Create account | Repeated character is accepted in Employee Name | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13 | [14 empty] | Incorrect Documentation
55 | Validation | Create account | ACE number is limited to 4 characters. Should be increased | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13 | [14 empty] | Scope Change
56 | Filter | FIlterdropdown | Role is not filtered based on department | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13 | [14 empty] | Recommendation
57 | Validation | Email field | Error message in Email is not proper & specific | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13 | [14 empty] | Incorrect Test Data
58 | Validation | Filterdropdown | Project is displayed even when the user is TAC or Administrator | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
59 | Spelling mistake | Create account (Snack bar) | Snack bar message is not correct(spelling mistakes & punctuation) | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
60 | Validation | Login | Login button's hover effect is light in colour | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
61 | Validation | Login | Alert message should be changed. (Wait untill you receive a mail) | Closed | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
62 | Alignment | Add Department | Card is misaligned | Closed | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
63 | Alignment | Add Location | Card is misaligned | Closed | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
64 | Alignment | Add Project | Card is misaligned | Closed | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
65 | Alignment | Add Role | Card is misaligned | Closed | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
66 | Validation | Add Department | Repeated character is accepted as Department name (Ex: Javaaaaaa) | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
67 | Validation | Add Location | Repeated character is accepted as Location name (Ex: Kashmirrrrrrr) | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
68 | Validation | Add Project | Repeated character is accepted as Project name (Ex: rrrrrrrrrr) | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
69 | Validation | Add Role | Repeated character is accepted as Role name (Ex: rrrrrrrrrr) | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-13
70 | Sorting | Add Department | Newly added department is not displayed at the top of the department list | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-13
71 | Sorting | Add Location | Newly added location is not displayed at the top of the location list | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-13
72 | Sorting | Add Project | Newly added project is not displayed at the top of the project list | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-13
73 | Sorting | Add Role | Newly added role is not displayed at the top of the role list | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-13
74 | Correction | Manage Pool members | "Pool Member already exists in the given Pool Id" - Error message is wrong | Closed | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-14
75 | Alignment | TAC Create Invite page | Card is misaligned | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-14
76 | Validation | TAC - Create Invite page | Numbers/symbols are not accepted in Drive Name | Open | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-14
77 | Validation | TAC - Create Invite page | If Mode is online, Location is set to Not Applicable | Closed | Minor | Medium | System Testing | coding | Development | Release |  | 2022-07-14
78 | Functionality | Interviewer - Accept Invite page | Multiple time slots cannot be given for drive invite. Drive data vanishes after first slot is given | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-14
79 | Functionality | TAC - Manage Pool | Pool members cannot be added to a newly created pool | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-14
80 | Functionality | Interviewer Cancel Interview Page | Comment allows unlimited characters. Maximum boundary is not fixed | Open | Major | High | System Testing | coding | Development | Release |  | 2022-07-14