## Day 3(06-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Refining the Management Flow Diagram, Refining the TAC user stories and Brainstorming about the project with team | Creating User Stories for TAC and Interviewer and attended design pattern session | Round based Interview | 6 | 1.5
Darshana | Refining the overall user stories, Brainstorming about the project with team and rough flow for TAC | Creating User Stories for Management and attended design pattern session | Round based Interview | 6 | 1.5
Deepika | Refining the overall user stories, Brainstorming about the project with team and rough flow for TAC | Creating User Stories for Management and attended design pattern session | Round based Interview | 6 | 1.5
Gokul | Refining the Interviewer Flow Diagram and Brainstorming about the project with team | Creating User Stories for Interviewer and attended design pattern session | Round based Interview | 6 | 1.5
Kumaresh | Refining the TAC Flow Diagram,Refining the Interviewer user stories and Brainstorming about the project with team | Creating User Stories for TAC and Worked on Flow Diagram and attended design pattern session | Round based Interview | 6 | 1.5
Prithvi | Refining the TAC Flow Diagram and Brainstorming about the project with team | Created Flow Diagram for users and Wrote Functional Requirements and attended design pattern session | Round based Interview | 6 | 1.5
Remuki | Refining the overall user stories, Brainstorming about the project with team and rough flow for TAC | Creating User Stories for Management and attended design pattern session | Round based Interview | 6 | 1.5
Sheik Fareeth | Refining the Interviewer Flow Diagram,Refining the user stories and Brainstorming about the project with team | Wrote functional requiremets and attended design pattern session | Round based Interview | 6 | 1.5
Vinoth | Refining the Management Flow Diagram and Brainstorming about the project with team | Created Flow Diagram for users and Wrote Functional Requirements and attended design pattern session | Round based Interview | 6 | 1.5
Vishnu Prakash | Refining the user stories for TAC and Brainstorming about the project with team | Creating User Stories for TAC and attended design pattern session | Round based Interview | 6 | 1.5

## DAY 4(07-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | dependencies for Management | 30 min : Exploring Figma, 1 hr 30 min : Refined Interviewer flow (SCHEDULE ,VIEW) 1hrs :MANAGEMENT Prototype (Register,Login,Interview Ignored 1 hr : Attended Design Pattern Session 1hr 15 mins : Refined User Stories &Acceptance Criteria (Management)(8-11) | - | 4.15 | 1.15
Darshana | Prototype for creation of link for TAC, Acceptance criteria for TAC | Redefining Mangement flow(Registration,View profile & stats) [1 hrs], Prototype - Scheduled drive,Attended design pattern session(2.30),Exploring Figma | Round based Interview | 4.5 | 1.15
Deepika | Prototype for TAC dashboard, Constraints for TAC | 30 mins : Exploring Figma 1 hr : Redefining Mangement flow diagram(Drive invite, Scheduled interview) 1hr : Attended Design Pattern Session 2 hr : Prototype - Current drive ,Upcoming drive | Round based Interview | 4.5 | 1
Gokul | dependencies for Management | 1hr : INTERVIEWER Prototype (Interview Attended,Unused Slots ) 30 min : Exploring Figma 30 mins : MANAGEMENT Prototype (Interview Attended) 1hr : Attended Design Pattern Session 1hr : Refined User Stories & Acceptance Criteria (Management(1,2,3)) | Round based Interview | 6 | 1.5
Kumaresh | dependencies for Management & Cancellation for TAC | 30 mins: Refined TAC Flow Diagram 30 mins: Exploring Figma 1hr : Prototype for Interviewer-Interview Denied 1hr : Attended Design pattern Session(Abstract Factory) 1hr : Refined Prototype for Interviewer 1hr : Refined User Stories & Acceptance for Management(5-8) | - | 4 | 1
Prithvi
Remuki | Desigining pool,Notification cancel for TAC
Sheik Fareeth | Acceptence(8-13) , Dependencies(8-13) for interviewers | 30 mins : Exploring figma 30 min : Designed prototype for INTERVIEWER's Profile, 30 min : Prototype for interviewer's Interview History 1 hr : Prototype for Scheduled Interviews 1 hr : Attended Abstract factory session 1 hr : Refined User stories(1-7) 30 mins : Acceptance(1 TO 5) | - | 5 | -
Vinoth | Prototype for Interviewers | 30 mins : Refined Interviewer Flow diagram 30 mins : Exploring figma 2 hr : Redefined Prototype for interviewer and management 1 hr : Attended Design Factory Session 1 hr : Prototype for interviewer Today's and scheduled interviews | - | 5 | 1
Vishnu Prakaash R | Recalling and exploring on prototype model | 30 mins: Userflow diagram discussion and implementation 1 hr : Figma and Diagrams net practice -self exploration 2.5 hr : Creating ADMIN'S userflow, constraints, dependencies, acceptance criteria. 30 mins : preparing for abstract factory ppt and code 1hr : presenting design pattern method, at hydra | Round based Interview | 4 | 2.5

## DAY 5 (08-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | - | 30 min : Explored Git Desktop, 1 hr 15 min : Dependencies and Constraints for management 1hrs 45 mins :MANAGEMENT Prototype (Dashboard Categories , Pool Members ' Scheduled Interviews Ignored) Refined navigatability 1 hr : Attended Design Pattern Session | - | 3 | 1.5
Darshana | Prototype | Acceptance criteria for TAC-1hr Design pattern session -1hr Refinded TAC prototype- 2hr Design pattern -30 min |  | 4.5 | 1.15
Deepika | Prototype for current flow | 1 hr : Constraints for TAC 1hr : Attended Design Pattern Session 1 hr : Prototype for Current drive ,Upcoming drive 1 hr : Prototype for Create Invite |  | 4 | 1
Gokul | dependencies for Management | 30 mins : Explored Git 2 hr: Refined Management Prototype 1hr : Attended Design Pattern Session(Builder and Protoype) 1hr : Softskills | Round based Interview | 2.5 | 2
Kumaresh | - | 30 Mins: Explored Github Desktop 1 Hr 30 Mins: Refined Prototype for Interviewer 1 Hr: Design pattern session(Builder and Prototype) 1 Hr: Softskills session 1 Hr 30 Mins: Refined Management Prototype and its flow. | - | 3.5 | 2
Prithvi | Dependencies for Interviewer (7-13) | 1hr : Explored git and git desktop 1hr : Refined Prototype for Interviewer-Dashboard 1hr : Attended Design pattern Session(Builder and Prototype pattern) 1hr : Refined Prototype for Interviewer 1hr : Acceptence criteria and constrains for interviewer | - | 4 | 1
Remuki | Desigining pool,Notification cancel for TAC | 1 hr : Dependencies for TAC 1 hr : Prototype for TAC ,Create pool ,Manage pool 1 hr : Attended Design Pattern Session 1 hr : Soft Skills Session 1 hr : Prototype for TAC
Sheik Fareeth | Acceptence(8-13) , Dependencies(8-13) for interviewers, Prototype | 30 mins : Explored git and git desktop 1hr : Refined Prototype for Interviewer-10 slide 1hr : Attended Design pattern Session(Builder and Prototype pattern) 1hr : Refined Prototype for Interviewer 1 hr : soft skill sessions | - | 4.5 | -
Vinoth | Prototype for Interviewers | 2 hr : Correction in Interviewer Prototype 1 hr : Redefined Prototype for interviewer and management 1.5 hr : Attended Design patternSession 1 hr : Aligned Interviewer and management Prototype | - | 4 | 1.5
Vishnu Prakaash R | Exploring on Git and Git Desktop | 2 hr: Creating prototype for admin using FIGMA 1.5 hr : Attending Design pattern session (Prototype and Builder design) 1 hr : preparing for review and self exploration 2 hr: Understanding the overall flow, Ensuring changes which were said yesterday(Drop down for project,Phone number and role, scroll page,back button,adding filter,interview denied list.) | - | 4 | 2.5

## DAY 6 (09-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Absent | Absent | - | 0 | 0
Darshana | Data Model | Brainstorming -30 Mins College Project review- 1 hour Prototype and Acceptance criteria for TAC- 1hr | - | 1 | 1.5
Deepika | Data Model | 30 mins : Brainstorming with team 1 Hr : Prototype for Dashboard in TAC 1 Hr : Refining the TAC prototype (Alignment,Naming) | - | 2.5 | 0
Gokul | Data Model | 30 min: Brain Storming with team 1.5 hr: Refined management Prototype(Dashboard,Profile) 30 min: Refined management prototype(alignment) | - | 2.5 | 0
Kumaresh | Data Model | 30 min: Brain Storming with team 1.5 hr: Refined management Prototype 30 min: Refined management and interviewer prototype(alignment) | - | 2.5 | 0
Prithvi | Dependencies for Interviewer (7-13),Data Modelling | 30 mins : Brain stroming with Team 1 hr : Refining the TAC Prototype ( Dash board , Profile ) 30 mins : TAC Prototype Page Alignments 30 mins : Refined TAC Prototype (Home page) | - | 2.5 | 0
Remuki | Desigining pool,Notification cancel for TAC | 30 min :BrainStroming 1 hr : Dependencies for TAC 1 hr : Prototype for TAC | - | 2.5 | 0
Sheik Fareeth | Acceptence(8-13) , Dependencies(8-13) for interviewers, Prototype | 30 mins : Brain stroming 1 hr : Refining the Interviewers Prototype ( Dash board , Profile , Navigations ) 1 hr : TAC ( Creating pools , Pool details prototype , and refining Slide ) | - | 2.5 | 0
Vinoth | Data Model | 30 mins : Brainstroming 1 hr : Added page navigation for interviewer and TAC prototype. 1 hr : Aligned TAC and Interviewer prototype | - | 2.5 | -
Vishnu Prakaash R | Exploring on Data models | 30 mins - Brainstorming 1.5 hour - College Project review preparation and PPT 1 hour - Refined Prototype for ADMIN | - | 1.5 | 1.5

## Day 7 (11-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Data Model | 1 Hr 30 Mins: Brainstorming 1 Hr :Refined User Stories,Acceptance Criteria 1 Hr 30 Mins :RefinedDependancies and Constraints(Management,Half of TAC) | - | 4 | 0
Darshana | Data Model | 1 Hr 30 Mins: Brainstorming 1 Hr 30 mins: Discussed Data Modelling 1 Hr :Entered attribute values(Employee,TAC) | - | 4 | 0
Deepika | Data Model | 1 Hr 30 mins : Brainstorming with team 1 Hr 30 mins : Prototype for TAC-(Create,View & Delete Pool - 6 slides) 1 Hr : Redefined the overall prototype for TAC | - | 4 | 0
Gokul | Data Model | 1Hr 30Mins:Brainstorming 2Hr:Data Model(7 Entities) | - | 3.5 | 0
Kumaresh | Data Model | 1 Hr 30 Mins: Brainstorming with team 1 Hr :Refined User Stories,Acceptance Criteria 1 Hr 30 Mins :Refined Dependancies and Constraints(Management,Interviewer) | - | 4 | 0
Prithvi | Refine Data Model(Should add Interface) | 1 Hr 30 Mins: Brainstorming with team 1 Hr 30 mins:Data Modelling(Overview,Response table) 1 Hr : Refined Data-Model(Added Invites ,Response Type table) | - | 4 | 0
Remuki | Data Model | 1 hr 30 minutes : Brainstroming with the team 2 hr : Refined the Prototype for TAC ( Edit pool ) 30 minutes : Alligingment. | - | 4 | 0
Sheik Fareeth | Data Model | 1 hr 30 mins - Brain Stromming 30 Mins - Adding New slides to TAC ( Upcoming drives, notifications, scheduling drives - 5 slides ) 1 hr 30 mins - Building Data model In draw.io ( 7 Entities ) 30 Mins - Re refining Interviewers scheduled drive cancellation | - | 4 | 0
Vinoth | Data Model | 1Hr 30 mins : Brainstroming 1 hr : Discussed Data modeling 1 hr 30 mins : Entered attributes for data model(Pool managing, invites, interviews) | - | 4 | -
Vishnu Prakaash R | Data Model | 1hr: Brainstorming with Team 45m: Adding pages and refining flow on ADMIN access. 45m: Entered attribute values for drive and discussing logic with Team mates. 30m: College project discussion - review call | - | 3.5 | 0.5

## Day 8 (12-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Data Model | 1 Hr 30 Mins: Brainstorming with team 1 Hr : Refined TAC prototype(Create pool and add members) 1 Hr :RefinedRefined TAC prototype(view and manage pool(add,remove members)) 1 Hr :Brainstorming | - | 4.5 | 0
Darshana | Data Model | 1 Hr 30 Mins: Brainstorming 2 Hr :Entered attribute values(Employee,Pool) 1 Hr :Brainstorming | - | 4.5 | 0
Deepika | Data Modelling | 1 Hr 30 mins : Brainstorming with team 2 Hrs : Entered Attribute values for Project & Drives 1 Hr :Brainstorming with team | - | 4.5 | 0
Gokul | Data Model | 1hr 30mins:Brain stroming with team 1hr30mins: Refined Datamodel(response and cancellation) 30mins:session with anitha 1 Hr :Brainstorming | - | 4.5 | 0
Kumaresh | Data Model | 1 hr 30 mins - Brain Stromming 1Hr:Preparing for code review 1hr :Attending review 30mins:session with anitha 1 Hr :Brainstorming | - | 5 | 0
Prithvi | Refine Data Model(Should add Interface,Relationship) | 1 Hr 30 Mins: Brainstorming with team 1 Hr 30 mins:Refined Data Modelling(Interview,EmployeeResponse table) 30 Mins : Added Data-Model(Added Cancelled Interview, Cancellation type table) 1 Hr :Brainstorming | - | 4.5 | 0
Remuki | Data Model | 1 hr 30 minutes : Brainstroming with the team 1 hr : Preparing for the Review 1 hr 30 min : Data Entry for Available member Table. 1 Hr :Brainstorming | - | 4 | 1
Sheik Fareeth | Data Model | 1 hr 30 mins - Brain Storming 45mins:Preparing for code review 45mins :attending review 30mins:session with anitha 1 Hr :Brainstorming | - | 4.5 | 0
Vinoth | Data Modeling(Methods) | 1 Hr 30mins: Brainstorming with team 1 Hr : Session with Rafi(Design patterns) 1 Hr : Meeting with Rafi(Review) 1 Hr : Edited data model tables 1 Hr : Worked on data entry table 1 Hr :Brainstorming | - | 5.5 | 1
Vishnu Prakaash R | Data Model | 1.5 HR: BrainStorming with Team 1 HR: Refined Admin Flow (Added pool deletion request from TAC) 1 HR: ANGULAR - self exploration 1 Hr :Brainstorming | - | 3.5 | 1

## Day 9 (13-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Exploring HTML,CSS(Basics,Syntax,tags,images,link,inline css) | 1 Hr : Brainstorming with team. 1 Hr 30 Mins: Session by Rafi 1 Hr : Re-Defined TAC Prototype(Remove members,Add Role,Remove Role). | - | 3.5 | 1.5
Darshana | Exploring Web API | 1 hr-Brainstorming 30 min-Entered attribute values 1 hr 30 min-Session with Rafi 1 hr-Operation for entity | - | 2.5 | 1.5
Deepika | Basics of Java Script | 1 hr : Brainstorming with team 30 minutes : Written methods for Entity 1 hr 30 mins : Session with Rafi 1 hr : College Project Review | - | 3 | 1
Gokul | HTML and Basics of Javascript | 1hr:Brain storming with team 30mins:prepared for Code Review 1hr30mins:session with Rafi 30mins:Refined and alligned TAC(add and delete department) 1hr:data modeloperation on drive | - | 4 | 0.5
Kumaresh | Exploring (HTML,CSS,JAVASCRIPT) | 1hr : Brainstorming with team 1hr : Redefined TAC Prototype (Add project,Remove Project,Alligned Navigation bar) 1hr 30m:Attended Raffi Sessions 1hr : Datamodel Operations(Employee) | - | 4.5 | 1
Prithvi | Have to explore more on Web Api Core(Middlewares) | 1hr : Brainstorming with team 30 mins : Explored on Database Normalization 1.30 hr: Added Relationship in Data Model 1.30 hr: Session (Design and Data Model) 30 mins: Worked on Operations on Entities(Employee,Drive Pool) | - | 5 | 0
Remuki | Data Model(Web ApI) | 1 hr : Brainstorming 1 hr : Preparing for Review 1 hr : Attending the review 30 minutes : Giving the operations for the model | - | 3.5 | 2
Sheik Fareeth | Introduction to Java Script | PROJECT : Brain Storming with team - 1 hr Design pattern Presentation ( Wrapper Pattern ) - 30 mins Session with Rafi - 1 hr 30 Mins Attended code review : 30 Mins NON - PROJECT : Explored basics of Web API - 30 Mins | - | 3.5 | 0.5
Vinoth | Data Modeling(Operations) | 1 Hr : Brainstorming with team 1 Hr 30 mins: Session with Rafi(Data modeling) 1 Hr : Explored normalization concepts 1 Hr : Edited data model tables | - | 4.5 | -
Vishnu Prakaash R | Angular:Architecture, components and Templates. | 1 hr : Brainstorming with Team Mates 1.5 hr : Angular pakage installation (rxjs,schematics/update) and version update. 15 mins : Break 1 hr : Admin flow - Evaluation and Novelty 15 mins : The Hindu article - NEWS 1.5 hr : General Session (GOALS) - with Rafi 15 mins : IDLE 1 hr : Lunch Break 15 mins : Pushed updated timesheet on GIT. | - | 2 | 5

## Day10 ( 18-04-2022 )
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Exploring CSS(External,Javascript,type Script) | 1 Hr : Brainstorming with team. 1 Hr 30 Mins:JavaScript (basics,syntax) 1 Hr 30 Mins:JavaScript 15 mins : installed Typescript in Vs code 1 Hr :Typescript(basics,syntax) | - | 1 | 4
Darshana | Exploring Web API | 1 hr-Brainstorming with team 1hr-HTTP protocol 1hr-Explored Web API 1hr-Written services for TAC 1 hr-Exploration TypeScript | - | 5
Deepika | Preparation of High Level Design, Typescript | 1 Hr: Brainstorming with Team 1 Hr 30 mins : Exploration on Javascript & Typescript 1 Hr : Worked on Designing Layout 1 Hr 30 mins : Written Services for Interviewer & TAC | - | 5
Gokul | Javascript | 1hr : brain storming with team 3.5hr:exploredjavascript(variables,Function,Object,String and String methods) | - | 4.5 | 0
Kumaresh | Exploring (JAVASCRIPT,TYPESCRIPT & ANGULAR) | 1hr : Brainstorming with team 1hr 30 mins: Exploring Java Script (basic) 1hr 30 mins:Exploring Type Script (basic) | - | 1 | 3
Prithvi | High Level Design | 1hr : Brain Storming with team 1hr : Explored on WebAPI Core 1hr : Explored on Entity Framework Core 1hr : Worked Out Migrations in Code-First Approach 1hr : Worked on ImageServiceWebApi | - | 5 | 0
Remuki | Data Model(Web ApI) | 1 hour : Brainstorming 30 minutes : Exploring HTML 30 minutes : Exploring CSS 1 hour : Exploring on Javascript and TypeScript 1 hour :Exploring on WEB API | - | 4 | -
Sheik Fareeth | Introduction to Java Script | PROJECT : Brain Storming with team - 1 hr Exploring basics of VS Code - 1.5 hr Exploring basics of Asp.net MVC Core - 1 hr Exploring basics of Javascript - 30 mins Listing out the Services for Users (TAC, Interviewer ) - 1 hr | - | 5 | 0
Vinoth | Migration (Foreign key relation) | 1 hr : Brainstorming 2 hr : exploration on webapi 1 hr : exploration on entity framework 1 hr : Tried migration on code first approach 1 hr : exploration on typescript | - | 5 | -
Vishnu Prakaash R | Layout creation and Implementation | 1 hr - Brainstorming with Team mates 2 hr - Angular (Data binding and Directives) 2 hr - Typescript(Basic syntac, variables,Types and Operators) 0.5 hr - HLD Sample Documentation - overall view | - | 5.5 | -

## Day11 ( 19-04-2022 )
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Exploring CSS(External,Javascript,type Script) | 1 Hr : Brainstorming with team. 1 Hr :JavaScript (functions,strings,arrowmethods etc..) 1 Hr 15 Mins:JavaScript(Sample Excercises basics) 1 Hr :Typescript(functions) 1hr:Exploring Angular(Overview,Components) | - | 1 | 4.25
Darshana | Exploring Web API | 1 hr-Brainstorming with team 2hr-working on Layout 1hr-Explored on TypeScript 1hr -Explored on Web API | - | 5
Deepika | Working on Layout, Exploration on Angular | 1 Hr: Brainstorming with Team 1 Hr 30 mins : Designed Home Layout page 1 hr : Attented Review with Anitha 30 mins : Explored Typescript 1 Hr : Exploration on Angular | - | 4 | 1
Gokul | Exploring on Angular | 1hr : brainstorming with team 1.5hr:Explored javascript(number methods,Array methods and Classes) 1.5 hr: Explored basics of Angular(Components,Databinding) | - | 4 | 0
Kumaresh | Exploring (JAVASCRIPT,TYPESCRIPT & ANGULAR) | 1hr : Brainstorming with team 1hr : Exploring Java Script (basic) 1hr :Exploring Type Script (basic) 1hr:Exploring Angular(Basics) 1hr:Refined layout | - | 2 | 3
Prithvi | Have to explore more on Angular Concepts | 1hr : Brainstorming with team 1hr : Typescript Basics 2hr : Explored on Angular Basics(Components,Templates) 1hr : Internal Review with Anitha 2hr : Worked on angular components | - | 7 | 0
Remuki | Data Model(Web ApI) | 1 hour : Brainstorming 2 hr : Designing the layout 1 hr : Exploring on typescript 1 hour :Exploring on Web Api | - | 5 | -
Sheik Fareeth | Typescript & Angular | PROJECT : Brain Storming with team - 1 hr Prepared Services & View Models - 1 hr Prepared HLD - 2 hr Explored Basics of Typescript & Angular - 1 hr | - | 5 | 0
Vinoth | Exploring Angular | 1 hr : Brainstorming 2 hr : exploration on angular basics 1 hr : exploration on entity framework 1 hr : exploration on angular components 1 hr : Attented Review with Anitha 1 hr : Explored typescript |  | 6 | 1
Vishnu Prakaash R | OVERVIEWING HLD | 1 hr : Brainstorming with Team 1 hr : Entity framework(Datamodel and DBcontext) 1 hr : Angular(Pipes,Dependency Injection,components recall,services) 1 hr : Web API (RESTful services) 1 hr : Typescript (static typing, interfaces) | - | 4 | 1

## Day12 ( 20-04-2022 )
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Exploring on Angular | 1 Hr : Brainstorming with team. 1 Hr :Attended Softskill session(Acceptance,problem solving). 1Hr : ExploringTypeScript(Conditional Statements,Switch Case,Looping Statements) | - | 1 | 2
Darshana | Exploring Typescript | 1 hr-Brainstorming with team 1.2 hrs-Attended Soft skill session(Problem solving and thinking) 30 min-Explored on Typescript (Switch,Arrays) 30 min-Alignment and correction in HLD | - | 2 | 1.2
Deepika | Working on Layout | 1 Hr : Discussion with team 1.2 Hrs : Attended Soft skill session - Acceptance & problem solving 30 mins : Refined the Layout for HomePage 30 mins : Exploration on Typescript(Operators,Arrays,Tuples) | - | 2 | 1.2
Gokul | Exploring on Angular | 1hr : brainstorming with team 1.2hr:Softskill session with jaya(Acceptance and Thinking) 1hr:prepared for code review 45mins:Code Review | - | 4 | 0
Kumaresh | Exploring (JAVASCRIPT,TYPESCRIPT & ANGULAR) | Absent | -
Prithvi | Have to explore more on Angular Concepts(Two way binding) . Start API Implementation | 1hr : Brainstorming with team. 1.2 hrs : Softskill session with Jaya(Problem solving, Acceptance and Thinking ) 1hr : Revised Typescript(Primitive data types, arrays, loops, classes, object and functions) | - | 2 | 1.2
Remuki | Data Model(Web ApI) | 1 hour : Brainstorming with team 1 hr : Attended the soft skills session (Presentation on challenges faced in our life ) 1 hr : Exploring on javascript and typescript exercises. | - | 3 | -
Sheik Fareeth | Typescript & Angular | 1 hour : Discussion with the team 1.2 hrs : Attended the soft skills session with HR team 1.5 hr : Explored on Basics of Javascript ( Script tags, Inlining,Syntax & Popup Messages, DOM ) | - | 2.5 | 1.2
Vinoth | Exploring angular | 1 hr : Brainstorming 1.2 hrs : Softskills 1 hr : exploration on typescript(Loops) |  | 2 | 1.2
Vishnu Prakaash R | Exploring framework types - web framework, component based,Object relational mapping. | 1 hr : Brainstorming with Team mates 1 hr : Softskill session 1.5 hr : Web API- Forms, history and storage | - | 2.5 | 1

## Day13 ( 21-04-2022 )
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Exploring on Angular | 8:15AM-8:20AM -Checking Mails. 8:45AM-9:00AM -Brainstorming with team. 9:00AM-10:30AM -Worked on MVC Application(for Code Review) 10:30AM-10:45AM-Break 10:45AM-11:45AM- Prepared Non Functional requirements 11:50AM-12:55PM-Brushed Up Concepts(for Code Review) | - | 1 | 2.2
Darshana | Dependencies for theTAC and Admin | 8:45-9:00 - Brainstorming with team 9:00-10:30 - Created Architecture diagram in entity level for TAC and Admin 10:30-10:50 -Break 11:00-12:20 - Created Architecture diagram in Service level for TAC and Admin 12:20-12:45 - Created HLD document | - | 3.2 | 0.2
Deepika | Working on Layout | 8:45-9:00 - Brainstorming with team 9:00-10:00 - Referred Bootstrap and designed common layout 10:15-10:50 - Proxy Pattern session with Rafi 10:50-11:00 - Break 11:00-12:10 - Designing Layout for Dashboard | - | 2.2 | 40mins
Gokul | Angular | 8.45-9.00Am:Brainstorming with team 9.00-10.00Am:Refined opertions in logical diagram(drive,poolmember) 10.10-11.10Am:Meeting with Rafi(Chain of Responsibility) 11.30-12.30Pm:Refined operations in Logical Diagram(department,Available member,role) | - | 3.15 | 0
Kumaresh | Exploring (JAVASCRIPT,TYPESCRIPT & ANGULAR) | Absent | -
Prithvi | Have to explore more on Angular Concepts(Two way binding) . Have to start working on Api Implementations | 8.45 to 9.00 am : Brainstorming with team 9.10 to 10.30 am : Refined Drive entity, Location Entity , Response Entity Operations 11.00 to 12.30 am : Coded Services in Visual Studios(All Services) | - | 3.2 | 0
Remuki | Data Model(Web ApI) | 8:45 to 9:00 - Brainstorming 9:00 to 9:30 - Exploring on bootstrap 9:30 to 10:30 - Desiging the Layout for TAC home 10:30 to 10:45 - Break 10:45 to 12:30 - Continuing on desiging the layout. | - | 3.5 | -
Sheik Fareeth | Dependencies for the 2 Users (Interviewer, Management) | 8:45-9:00 - Brainstorming 9:00-10:30 - Created Architecture diagram in entity level for interviewer and management. 10:30-10:50 -Break 11:00-12:20 - Created Architecture diagram in Service level for interviewer and management. 12:20-12:45 - Created HLD document | - | 3.2 | 0.2
Vinoth | Have to Learn and work on WebAPI | 8.45 am - 9.00 am : Brainstorming with Team 9.00 am - 10.30 am : Added operations(available responses, Employee) 10.45 am - 11.30 am : Refined operations (Project, Departement,cancellation reason) 11.30 am - 12.30 am : Refined operations in Drive model and aligned Logical Diagram 1.30 - 2.30 : Refined Operations 2.30 - 3.30 : Discussed nfr and system architecture 2.50 - 4.00 : Review with Rafi (Data model operations, NFR) 4.30 - 5.00 : Discussed MOM |  | 6.5 | 0
Vishnu Prakaash R | Seeking for more NFR and Pain points, Interactions. | 8.45 am - 9.00 am : Discussion with team mates. 9.00 am - 10.15 am : Exploring on NFR and processing raw data. 10.15 am - 11.15 am : Coverting Raw data into Sheets(NFR). 11.15 am - 11:30 : Break and clarification (Total number of NFR) 11:30 am - 12.00 pm : shallow (sample) and deep (final) 12.00 pm - 12.15 pm : Clarity about NFR, Refinement of flow. | - | 3 | -

## Day14 ( 22-04-2022 )
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Exploring on Angular | 8:15AM-8:20AM -Checking Mails. 8:45AM-9:00AM -Brainstorming with team. 9:00AM-9:10AM -Updated MOM 9:00AM-10:30AM -Worked on Layout(DashBoard) 10:30AM-10:45AM-Break 10:45AM-11:50AM -Worked on Layout(DashBoard) | - | 1 | 2.2
Darshana | Table creation & Database diagram | 8:45-9:00 - Brainstorming with team 9.00-9.30-Studied layered pattern architecture 9.30-10.30 -Created system architecture diagram 10.40-11.00-Break 11.10-12.30-Created tables in MSSQL( Employee, Role, Department, Project, Pool, Pool Members, Drive)1:00-2:00-Lunch 2:00-3:15-Discussed about Operations and Web API for our project 3:30-4:10-Review with Rafi 4:10-4:30-Break | - | 3 | 20 mins
Deepika | Working on Layouts | 8:45-9:00 - Brainstorming with team 9:00-9:30 - Done Corrections in Main Layout Page 9:30-10:30 - Designed Layout for Profile Page 10:30-10:45 - Break 10:45-11:30 - Layout for Dashboard 11:30-12:15 - Prepared Layout for Manage Department1:00-2:00 - Lunch 2:00-3:00 - Discussed about web API for our project 3:00-4:00 - Review with Rafi 4:00-4:15 - Break | - | 3 | 15 mins
Gokul | Interactions | 8.45Am-9.00Am Brainstorming with team 9.00Am-10.00Am Explored on webapi (what is WebAPI) 10.30Am-11.30Am Refined NFR 1:00-2:00-Lunch 2:00-3:15-Discussed about Operations in data model 3:30-4:10-Review with Rafi 4:10-4:30-Break | - | 4 | 0
Kumaresh | Exploring (JAVASCRIPT,TYPESCRIPT & ANGULAR) | 8:45-9:00 - Brainstorming with team 9:00-9:30 - Refined in Main Layout Page 10:30AM-10:45AM-Break 9.30-1:00 - Layout for Current Drives | -
Prithvi | Have to explore more on Angular Concepts(Two way binding) . Have to start working on Api Implementations | 8.45 to 9.00 am (15mins): Brainstorming with team 9.10 to 10.30 am (1hr 20mins) : Refined Drive entity, Location Entity , Response Entity Operations 11.00 to 12.00 (1hr): Refined Employee Operations 12.00 : absent | - | 2.5 | 0
Remuki | Working on Layout | 8:45 to 9:00 - Brainstorming 9:00 to 10:00 - Desiging the common layout page 10:00 to 10:30 -Desiging the layout page for TAC(Home) 10:45 to 11:00 -Break 11:00 to 12:30 - Continuation on the desining the page for upcomming drives. | - | 3.5 | -
Sheik Fareeth | Dependencies for the 2 Users (Interviewer, Management) | 9:30to 10:00 - Brainstorming with team 10:00 to 10:30 - Correcting System Architecture Diagram ( Rearranging Layers & DB ) 10:30 to 10:45 Updating MOM 10.45 to 11.15-Studied basics of web API ( how to create a web api project in VS Code 11.15to 11.45-Break 11.45 to 12.30 - Studied how to connect EF with Web API Project | - | 3 | 30 Mins
Vinoth | Have to Learn and work on WebAPI | 8.45 - 9.00 : Brainstorming with Team 9.00 - 10.40 : Updated data model (Drive) 11.00 - 12.30 : refined data model (Pool, Pool member, Location, Department, Project) |  | 3.5 | 0
Vishnu Prakaash R | Interactions. | 8.45 am - 9.00 am : Brainstorming with team mates. 9.00 am - 10.00 am : Clear Refinement of NFR (Replaced Subjective words). 10.00 am - 10.30 am : Datamodel Understanding - 10.30 am - 10.45 am : BREAK 10.45 am - 11.15 am : Google API - calender (Event,calender list, settings) and Google workspace. 11:15 am - 12:15 pm : converting sheets to document format. (NFR) | - | 2.5 | 0.5

## Day15 ( 23-04-2022 )
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Exploring on Angular | Absent | - | 1 | 2.2
Darshana | Exploring EF core | 9:00-9:30-College Meeting (Project updation details) 9:30-10:15-Designed Layout for Manage pool 10:20-10:40-Break 10:40-11:15-Edited Common layout by comparing the prototype 11:15-11:30-Discussion with team 11:30-12:00-Corrected conflicts in css | - | 2.1 | 50 mins
Deepika | Exploring Angular | 9:00-10:00 - Designed layout for Manage Pools 10:00-11:00 - Layout for Fresher's Pool(In Progress) 11:00-11:15 - Break 11:15-11:30 - Discussion with team 11:30-12:30 - Merged CSS files & uploaded in GitHub | - | 3.15 | 15 mins
Gokul | Exploring EF core | 9:00-10:15 - Exploration on EF core(Migration, Annotation) 10:15-11:00 - College Project Discussion 11:00-11:15 - Break 11:15-11:30 - Discussion with team 11:30-12:30 - Layout for Response in Upcoming Drives | - | 2.5 | 45 mins
Kumaresh | Exploring WEB API | 10:00-11:00 - Refined Current Drives Layout 11:00-12:00 - Attented College Review 12:00-12:30 - System Allocation 2:00-3:00 - Notifications Loyout | -
Prithvi | Have to work on Api Implementations | 9:30am to 10:00am : Brainstorming with team 10.10am to 11.30 am : Implemented Role Service and Role Model for API 12.00pm to 12.30pm : Worked on EF Code First for Role Model class 12.30pm to 1.00 : System Allocation. 1.45pm to 3.00pm : worked on Data Acess layer 3.30pm to 4.15pm : Meeting with Rafi(changes in Operations and Api ) | - | 5.5 | 0
Remuki | Working on Layout | 9:30 to 10:00 -Brainstorming with team 10:00 to 10:30 - Working on layout for TAC's Upcoming drive. 10:30 to 11:30 - Session with rafi. 11:30 to 11:45 - Break 11:45 to 12:30 - continued on desiging the upcoming drives page . 2:00 to 3:00 - Layout on upcoming drives. 3:00 to 3:30 - Idle 3:30 to 4:00 - Review with rafi . | - | 1.5 | 1.15
Sheik Fareeth | Designing Layout | 9:30to 10:00 - Brainstorming with team 10:00 to 10:30 - Correcting System Architecture Diagram ( Rearranging Layers & DB ) 10:30 to 10:45 Updating MOM 10.45 to 11.15-Studied basics of web API ( how to create a web api project in VS Code 11.15to 11.45-Break 11.45 to 12.30 - Studied how to connect EF with Web API Project 1.00 to 2.00 - Lunch 2.00 to 3.00 - How to use Postman App ( get post put methods, Using api's ) 3.00 to 3.30 - Idle 3.30 to 4.00 - Review Meeting with Rafi | - | 3 | 30 Mins
Vinoth | Have to Learn and work on WebAPI | 9:30am to 10:00am : Brainstorming with team 10.30am to 12.30 am : Reviewed Data model 12.30pm to 1.00 am: System Allocation 1.45 pm - 3.15 pm : Refined services 3.30 pm - 4.10 pm: review with rafi(data model, WebApi, layout) |  | 6.5 | 0
Vishnu Prakaash R | Overviewing interactions | 8.45 am - 9.00 am : Discussion with team mates. 9.00 am - 10.00 am : NFR _ REfinement 10.00 am - 10.30 am : Datamodel Understanding - 10.30 am - 10.45 am : BREAK 10.45 am - 11.15 am : Studying Roadmap to DOTNET 11:15 am - 12:15 pm : converting sheets to document format. (NFR) 2.30 pm - 3.30 pm : Meeting with Rafi | - | 4.5 | 2.5

## Day16 (25-04-2022) (2)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Working On Layouts(Remove Pool) | 8:15AM-8:20AM-Checking Mails. 8:40AM-10:30AM -Worked on Layout(CreatePool) 10:30AM-10:45AM-Break 10:45AM-11:15AM -Refactored(Naming ) Common Css file. 11:15AM-11:30PM-Brainstorming with team. 11:30AM-12:50PM -Refined Layout(DashBoard) | - | 1 | 2.2
Darshana | Exploring WEB API | 9:30-10:00 -Brainstorming with team 10:00 -11:20-Reviewed and Refined Data model 11:20-11:40-Break 11:45-12:20-Continued Refining the data model 12:20-12-:50-System Allocation | - | 2.2 | 50 mins
Deepika | Working on Layouts(Interviewer) | 9:30-10:00 - Brainstorming with Team 10:00-10:30 - Done corrections in Profile Layout 10:30-11:30 - Designed Layout(Manage Department,Add & Remove Dpt) 11:30-11:45 - Break 11:45-12:00 - Dashboard Layout for Interviewer(In progress) 12:00-12:30 - System Allocation | - | 2.15 | 45 mins
Gokul | Web API(RESTful) | 9:30-10:00 -Brainstorming with the team 10:00-10:30 - Explored How to create web API project 10:30-10:45 - Break 10:45-12:00 - Explored on web API(RESTful,SOAP) 12:00-12:30 - System Allocation | - | 2.5 | 45 mins
Kumaresh | Exploring WEB API and Working on Layouts | 9:00-10:30-Worked on Current Drives Layout 10:30-10:45-Break 10:45-11:45-Merged css file and correct some errors 11:45-1:00-Layout for Notifications 2:00-3:00-Layout for View Pool | -
Prithvi | Have to work on Api Implementations | 8.45am to 9.15am : worked on data acess layer for api 9.15am to 10.30 : worked on Data Factory Classes 10.30am to 10.45 : Refered sample API code in GitHub 11.15am to 12.45 : worked on exception handling for api. 1.30pm to 2.00 : reviewed my api implementation | - | 4 | 0
Remuki | Working on Layout | 10:00 to 11:00 - working on layout for home. 11:00 to 11:15 - Break 11:15 to 11:30 - Discussion with team 11:30 to 1:00 - working on the layout page for upcoming drives. | - | 3 | 1.15
Sheik Fareeth | Entity Framework | 8.45 to 9.00 - Updating MOM & Checking Mail 9.00 to 10.00 - Correcting Mistakes in Data model ( Audit fields for Employee, separating as single methods ) 10.00 to 10.45 - Analysing and Correcting Prototypes of Admin regarding Data models (all slides) 10.45 to 11.15 - Break 11.15 to 11.30 - General team Discussion 11.30 to 12.30 - Created prototype for Admin ( final version ) | - | 3 | 30 Mins
Vinoth | Working on Register screen | 8.45 am - 10.45 am : Corrections done in Data model and Prototype 11.15 am - 12.45 pm : register layout 1.15 pm - 2.30 pm : Refined Services(Role, Department, Employee, Drive, Pool, Location) |  | 4 | 0
Vishnu Prakaash R | Should focus on Angular and Interactions | 8.45 am - 9.00 am : checking mails 9.00 am - 10.15 am : Regulatory details and calculation for Scalability (Requests)- NFR 10.15 am - 10.45 am : Identifying common layout from TAC page 10.45 am - 11.00 am : BREAK 11.00 am - 11.30 am : Cloning GitHub repository to VS code and Checking whether IIS is installed or not. 11.30 am - 11.45 pm : Individual responsibility (Discussion with Team) - ANGULAR 11.45 am - 12.45 pm : Recalling angular concepts 12.45 pm - 1.30 pm : BREAK 1.30 PM - 2.30 PM: Github troubleshooting 2.30 pm - 3.30 pm : Meeting with Rafi | - | 4.5 | 2.5

## Day17(26-04-2022)
Column1 | Column2 | Column3 | Column4
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aravindhan Ra | Working On Layouts(Remove Pool) | 8:15AM-8:20AM-Checking Mails. 8:40AM-10:30AM -Worked on Layout(CreatePool) 10:30AM-10:45AM-Break 10:45AM-11:15AM -Refactored(Naming ) Common Css file. 11:15AM-11:30PM-Brainstorming with team. 11:30AM-12:50PM -Refined Layout(DashBoard) | - | 1 | 2.2
Darshana | Exploring EF Core | Yesterday 3:00-3:45-Review with Rafi(Project) 3:45-4:05-Break 4:20-4:40-Estimation session with Rafi 5:00-5:30-Written common and unique pages for the system 5:40-6:00-Discussion with team about Layouts Today 8:45-9:45-Designed Layout for Cancel Drive 9:45-10:45-Softskill Session with Savitha(Problem solving) 10:45-11:00-Break 11:00-12:15-Designed Layout page for Mangepools | - | 4 | 1.5
Deepika | Exploring Angular | 25/04/22 3:00-3:45 - Project Review with Rafi 3:45-4:05 - Break 4:20-4:40 - Session with Rafi(Estimation) 5:00-5:30 - Written the common & unique pages 5:40-6:00 - Discussion with team about designing Layouts 25/04/22 8:45-9:45 - Prepared layout for Cancel Invite 9:45-10:45- Softskills Session with Savitha(about Problem Solving) 10:45-11:00 - Break 11:00-12:00 - Corrected Layout page for Profile | - | 4.1 | 1
Gokul | Web API(RESTful) | 9:30-10:00 -Brainstorming with the team 10:00-10:30 - Explored How to create web API project 10:30-10:45 - Break 10:45-12:00 - Explored on web API(RESTful,SOAP) 12:00-12:30 - System Allocation | - | 2.5 | 45 mins
Kumaresh | Exploring WEB API and Working on Layouts | 9:00-10:30-Worked on Current Drives Layout 10:30-10:45-Break 10:45-11:45-Merged css file and correct some errors 11:45-1:00-Layout for Notifications 2:00-3:00-Layout for View Pool | -
Prithvi | Have to work on Api Implementations | 8.45am to 9.15am : worked on data acess layer for api 9.15am to 10.30 : worked on Data Factory Classes 10.30am to 10.45 : Refered sample API code in GitHub 11.15am to 12.45 : worked on exception handling for api. 1.30pm to 2.00 : reviewed my api implementation | - | 4 | 0
Remuki | Working on Layout | 10:00 to 11:00 - working on layout for home. 11:00 to 11:15 - Break 11:15 to 11:30 - Discussion with team 11:30 to 1:00 - working on the layout page for upcoming drives. | - | 3 | 1.15
Sheik Fareeth | Entity Framework | 8.45 to 9.00 - Updating MOM & Checking Mail 9.00 to 10.00 - Correcting Mistakes in Data model ( Audit fields for Employee, separating as single methods ) 10.00 to 10.45 - Analysing and Correcting Prototypes of Admin regarding Data models (all slides) 10.45 to 11.15 - Break 11.15 to 11.30 - General team Discussion 11.30 to 12.30 - Created prototype for Admin ( final version ) | - | 3 | 30 Mins
Vinoth | Working on Register screen | 8.45 am - 10.45 am : Corrections done in Data model and Prototype 11.15 am - 12.45 pm : register layout 1.15 pm - 2.30 pm : Refined Services(Role, Department, Employee, Drive, Pool, Location) |  | 4 | 0
Vishnu Prakaash R | Should focus on Angular and Interactions | 8.45 am - 9.00 am : checking mails 9.00 am - 10.15 am : Regulatory details and calculation for Scalability (Requests)- NFR 10.15 am - 10.45 am : Identifying common layout from TAC page 10.45 am - 11.00 am : BREAK 11.00 am - 11.30 am : Cloning GitHub repository to VS code and Checking whether IIS is installed or not. 11.30 am - 11.45 pm : Individual responsibility (Discussion with Team) - ANGULAR 11.45 am - 12.45 pm : Recalling angular concepts 12.45 pm - 1.30 pm : BREAK 1.30 PM - 2.30 PM: Github troubleshooting 2.30 pm - 3.30 pm : Meeting with Rafi | - | 4.5 | 2.5